## project
Music Mixer
[7 empty] | Day Highlight: |  |  |  |  | 14 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete
[19 empty] | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| NAME | PLAN | PLAN | ACTUAL | ACTUAL | PERCENT
ACTIVITY | ASSIGNED TO | START | DURATION | START | DURATION | COMPLETE | Day
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Brainstorming | Parth, Het, Shubh | 1 | 1 | 1 | 1 | 100%
UML & RFP | Parth, Het, Shubh | 1 | 2 | 1 | 2 | 100%
Draggable | Parth | 2 | 1 | 2 | 1 | 100%
Recorder | Parth | 2 | 2 |  |  | 0%
Loop Library | Het | 4 | 3 |  |  | 0%
Beat Maker | Parth | 4 | 3 |  |  | 0%
Audio Recorder | Parth | 2 | 2 |  |  | 0%
Piano Maker | Shubh | 4 | 3 |  |  | 0%
Sequencer UI | Shubh, Parth, Het | 3 | 4 |  |  | 0%
Design Complete Milestone | bar: Day 1 to Day 20
Draggable (Coding & Testing) | Parth | 4 | 2 |  |  | 0%
Recorder (Coding & Testing) | Parth | 5 | 3 |  |  | 0%
Loop Library (Coding & Testing) | Het | 6 | 3 |  |  | 0%
Beat Maker (Coding & Testing) | Parth | 6 | 3 |  |  | 0%
Audio Recorder (Coding & Testing) | Parth | 5 | 3 |  |  | 0%
Piano Maker (Coding & Testing) | Shubh | 6 | 3 |  |  | 0%
Sequencer UI (Coding & Testing) | Shubh, Parth, Het | 4 | 5 |  |  | 0%
Code Complete Milestone | bar: Day 1 to Day 20
Integrated Testing | Shubh, Parth, Het | 9 | 4 |  |  | 0%
Software Packaging/Delivery | Shubh, Parth, Het | 12 | 1 |  |  | 0%
Project Complete Milestone (Beta Release) | bar: Day 1 to Day 20